## BOQ_blank_signed
Name of Work : Construction of 03 (Three) Nos Women Friendly Toilet with Rest room: Especially for Adolescent Girls with Civil, Sanitary, Electrification & Running water supply etc. at Ukhia upazila in Cox'sbazar District under RER project during the year 2026.
Dividion/District : Cox's Bazar
N.B.: Trying to change anything in the written columns is prohibited. Just insert your rates in the blank column.
1 | 2 | 3 | 4 | 5 | 6 | 7
Part "A" Civil Works : (All the items included VAT, Tax & profit)
Sl. No. | Description of Works | Quantity | Unit | Rate in Taka | Amount in Taka | Remarks
1 | Providing Site preparation, Layout and Demarcating lines, existing ground level (EGL), formation ground level (FGL), highest flood level (HFL), plinth level (PL). Setting and marking all pillars, markers, pegs etc. showing and maintaining reduced levels (RLs) including locating, establishing, protecting all public utilities within the premise of work and finally all to be presented in black and white etc. All complete as per direction and guidance of the Engineer in Charge. | 84 | Sqm |  | 0
2 | Earth Work in Excavation(Wash Block and Septic Tank.) in all kinds of soil for foundation trenches including layout, providing center lines, local bench-mark pillars, levelling, ramming and preparing the base, fixing bamboo spikes and marking layout with chalk powder, providing necessary tools and plants, protecting and maintaining the trench dry etc., stacking, cleaning the excavated earth at a safe distance out of the area enclosed by the layout etc. all complete and accepted by the Engineer-in-charge, subject to submit method statement of carrying out excavation work to the Engineer-in-charge for approval. However, engineer’s approval shall not relieve the contractor of his responsibilities and obligations under the contract. | 46.22 | Cum |  | 0
3 | Earth Filling (Wash Block Floor,Septic Tank Floor, Ramp Floor) in foundation trenches and plinth in 150 mm layer with earth available within 90 m of the building site to achieve minimum dry density of 95% with optimum moisture content (Modified proctor test) including carrying watering, leveling, dressing and compacting to a specified percentage each layer up to finished level etc. all complete and accepted by Engineer-in-charge. | 15.21 | Cum |  | 0
4 | Sand Filling (Wash Block Floor, Septic Tank Floor, Ram Floor,MHM Pit Floor,Inspection Pit Floor) in foundation trenches and plinth with sand (salt free) having min. F.M. 1.2 in 150 mm in layers including leveling, watering and compaction to achieve minimum dry density of 95% with optimum moisture content (Modified proctor test) by ramming each layer up to finished level as per design supplied by the design office only, all complete and accepted by the Engineer-in-charge | 17.88 | Cum |  | 0
5 | Single Layer Brick Flat Soling (Wash Block Floor,Septic Tank Floor, Ramp Floor,MHM Pit Floor,Inspection Pit Floor, foundation, stair with landing, base of B/W, apron etc.) in foundation or in floor with first class/picked jhama bricks (BDS 208) including preparation of bed and filling the interstices with local sand, leveling etc. complete and accepted by the Engineer-in-charge. | 61.99 | Sqm |  | 0
6 | Supplying and laying of Single layer polythene (Wash Block Floor,Septic Tank Floor, Ramp, foundation, base of B/W) sheet weighting one kilogram per 6.5 square meter in floor or anywhere below cement concrete complete in all respect and accepted by the Engineer . | 61.99 | Sqm |  | 0
7 | Reinforced Cement Concrete Works(Wash Block Roof Slab, Lintel,Septic Tank Slab, MHM Pit Slab,Inspection Pit Slab) with minimum cement (SCAN/SEVEN RING/CONFIDENCE) content relates to mix ratio 1:2:4 having maximum water cement ratio = 0.45 and minimum f'cr = 26 MPa, satisfying a specified compressive strength f'c= 19 MPa at 28 days on standard cylinders as per standard practice of Code ACI / BNBC, cement conforming to BDS EN-197-1-CEM-I, 52.5N, best quality salt free sand [50% quantity of best salt free local sand (F.M. 1.2) and 50% quantity of Sylhet sand or coarse sand of equivalent F.M. 2.2] and 20 mm down well graded picked jhama brick chips conforming to ASTM C-33 including conducting necessary tests, breaking chips and screening, making and placing shutter in position maintaining true to plumb, making shutter water-tight properly, placing reinforcement in position; mixing in standard mixer machine with hopper fed by standard measuring boxes, casting in forms, compacting by vibrator machine and curing at least for 28 days, removing centering-shuttering after specified time approved; including cost of water, electricity, other charges etc. all complete, approved and accepted by the Engineer-in-charge. | 6.62 | Cum |  | 0
8 | Reinforced Cement Concrete Works (Wash Block shelve Slab) at bath toilet with minimum cement (SCAN/SEVEN RING/CONFIDENCE) content relates to mix ratio 1:2:4 having maximum water cement ratio = 0.45 and minimum f'cr = 26 MPa, satisfying a specified compressive strength f'c= 19 MPa at 28 days on standard cylinders as per standard practice of Code ACI / BNBC, cement conforming to BDS EN-197-1-CEM-I, 52.5N, best quality salt free sand [50% quantity of best salt free local sand (F.M. 1.2) and 50% quantity of Sylhet sand or coarse sand of equivalent F.M. 2.2] and 20 mm down well graded picked jhama brick chips conforming to ASTM C-33 including breaking chips and screening, making and placing shutter in position maintaining true to plumb, making shutter water-tight properly, placing reinforcement in position; mixing in standard mixer machine with hopper fed by standard measuring boxes, casting in forms, compacting by vibrator machine and curing at least for 28 days, removing centering-shuttering after specified time approved; including cost of water, electricity, other charges etc. all complete, approved and accepted by the Engineer-in-charge. | 0.05 | Cum |  | 0
9 | Mass concrete (1:2:4) (Wash Block ,Septic Tank , MHM Pit ,Inspection Pit,Ramp) in foundation or in floor with cement,sand (F.M. 1.2) and picked jhama brick chips including breaking of chips, screening, mixing, laying, compacting to required level and curing for at least 7 days including the supply of water, electricity, costs of tools & plants and other supply of water, electricity, costs of tools & plants and other charges etc. all complete and accepted by Engineer-in charge. (Cement: CEM-II / B-M) | 3 | Sqm |  | 0
10 | Supplying, Fabrication and Fixing (Wash Block Roof Slab, Lintel,Lintel Ring,Septic Tank Slab, MHM Pit Slab,Inspection Pit Slab)to detail as per design : ribbed or deformed bar (BSRM/ GPH) reinforcement (excluding laboratory test fees) for Reinforced concrete, produced and marked in accordance with BDS ISO 6935-2:2016 (or standard subsequently released from BSTI) including straightening and cleaning rust, if any, bending and binding in position with supply of G.I. wires, conducting necessary laboratory tests etc. (excluding splices or laps) complete in all respect and accepted by the Engineer-in-charge (Measurement shall be recorded only on standard mass per unit length of bars, while dia of bars exceeds its standard) Grade 500 (B500DWR: complying BDS ISO 6935-2:2016 / ASTM A615) ribbed or deformed bar | 616 | Kg |  | 0
11 | Supplying, Fabrication and Fixing (Wash Block shelve) 3 nos. ribbed or deformed bar (BSRM/ GPH) reinforcement for Reinforced concrete, produced and marked in accordance with BDS ISO 6935-2:2016 (or standard subsequently released from BSTI) including straightening and cleaning rust, if any, bending and binding in position with supply of G.I. wires, conducting necessary laboratory tests etc. (excluding splices or laps) complete in all respect and accepted by the Engineer-in-charge (Measurement shall be recorded only on standard mass per unit length of bars, while dia of bars exceeds its standard) Grade 500 (B500DWR: complying BDS ISO 6935-2:2016 / ASTM A615) ribbed or deformed bar | 12 | Kg |  | 0
12 | Supplying, Fabrication and Fixing (GF) ribbed or deformed bar (BSRM/ GPH) reinforcement for Reinforced concrete, produced and marked in accordance with BDS ISO 6935-2:2016 (or standard subsequently released from BSTI) including straightening and cleaning rust, if any, bending and binding in position with supply of G.I. wires, conducting necessary laboratory tests etc. (excluding splices or laps) complete in all respect and accepted by the Engineer-in-charge (Measurement shall be recorded only on standard mass per unit length of bars, while dia of bars exceeds its standard) Grade 500 (B500DWR: complying BDS ISO 6935-2:2016 / ASTM A615) ribbed or deformed bar | 362 | Kg |  | 0
13 | (20''Wall)-(Septic Tank) Brick works with first class bricks with cement sand (F.M. 1.2) mortar (1:6) in Foundation,Pillar, Grade Beam and plinth, filling the joints/interstices fully with mortar, racking out the joints, cleaning and soaking the bricks at least for 24 hours before use and curing at least for 7 days etc. all complete including cost of water, electricity and other charges and accepted by the Engineer-in-charge.(Cement: CEM-II/B-M) | 4 | Cum |  | 0
14 | (15''Wall)-(Septic Tank) Brick works with first class bricks with cement sand (F.M. 1.2) mortar (1:6) in Foundation,Pillar, Grade Beam and plinth, filling the joints/interstices fully with mortar, racking out the joints, cleaning and soaking the bricks at least for 24 hours before use and curing at least for 7 days etc. all complete including cost of water, electricity and other charges and accepted by the Engineer-in-charge.(Cement: CEM-II/B-M) | 4.17 | Cum |  | 0
15 | (10''Wall)-(Septic Tank and WASH Block) Brick works with first class bricks with cement sand (F.M. 1.2) mortar (1:6) in Foundation,Pillar, Grade Beam and plinth, filling the joints/interstices fully with mortar, racking out the joints, cleaning and soaking the bricks at least for 24 hours before use and curing at least for 7 days etc. all complete including cost of water, electricity and other charges and accepted by the Engineer-in-charge.(Cement: CEM-II/B-M) | 9 | Cum |  | 0
16 | (5'' Wall) - (Wash Block Wall, Septic Tank Buffalo Wall, MHM Pit Wall,Inspection Pit Wall) Brick works of width one brick or one and a half brick length of first class bricks with cement sand (F.M. 1.2) mortar (1:6) in super structure including raking out joints, filling the interstices with mortar, cleaning and soaking the bricks at least for 24 hours before use and washing of sand, necessary scaffolding, curing at least for 7 days etc. all complete (measurement to given as 250 mm width for one brick length and 375 mm for one brick and a half brick length) and accepted by the Engineer-in-charge. (Cement: CEM-II/B-M) In ground floor | 63 | Sqm |  | 0
17 | Supplying, Fitting and Fixing Country Made Floor Tiles (Fresh A Grade Tiles ,Tiles Size-12''x12'', Tiles Code-3HF10) homogeneous matt finished/ rustic floor tiles (AKIJ/ RAK/ GREAT WALL/ MIR) complying BDS ISO 13006: 2015, water absorption ≤ 0.5%, modulus of rupture (MOR) ≥ 27 N/mm2, irrespective of color &/or design, with 20 mm thick cement sand (F.M. 1.2) mortar (1:4) base and raking out the joints with white cement including cutting and laying the tiles in proper way and finishing with care etc. all complete and accepted by the Engineer-in-charge. The sample of tiles approved from EIC before installation. | 24 | Sqm |  | 0
18 | Supplying, Fitting and Fixing Country Made Glazed Wall Tiles (Fresh A Grade Tiles,Tiles Size-8''x12'', Tiles Code-W2008) (AKIJ/ RAK/ GREAT WALL/ MIR) Supplying, fitting and fixing country made glazed wall tiles complying BDS ISO 13006: 2015, irrespective of color &/or design, with 20 mm thick cement sand (F.M. 1.2) mortar (1:3) base and raking out the joints with white cement including cutting, laying and hire charge of machine and finishing with care etc. including cost of water, electricity and other charges complete in all respect and accepted by the Engineer-in-charge. (Cement: CEM-II/B-M). The sample of tiles approved from EIC before installation. | 30.2 | Sqm |  | 0
19 | Supplying, Fitting and Fixing 20 mm to 25 mm Thick Machine Made Cement Parking Tiles- (AKIJ/ RAK/ GREAT WALL/ MIR) (Stair and Ramp) having minimum compressive strength of 27 MPa, irrespective of color &/or design, with 20 mm thick cement sand (F.M. 1.2) mortar (1:4) base and making the joints carefully in true straight line including cutting, laying and hire charge of machine and finishing with care etc. including water, electricity and other charges complete in all respect and accepted by the Engineer-in-charge. (Cement: CEM-II/B-M). The sample of tiles approved from EIC before installation. | 7.83 | Sqm |  | 0
20 | Minimum 12 mm Thick Cement Sand (F.M. 1.2) (WASH Block Wall,Septic Tank Wall,MHM Pit Wall, Inspection Wall) Plaster (1:4) with fresh cement to both inner-and outer surface of wall, finishing the corner and edges including washing of sand, cleaning the surface, curing at least for 7 days, cost of water, electricity, scaffolding and other charges etc. all complete in all respect as per drawing and accepted by the Engineer-in-charge. (Cement: CEM-II/B-M) | 157.37 | Sqm |  | 0
21 | Minimum 6 mm Thick Cement Sand (F.M. 1.2) (Celling) Plaster (1:4) with fresh cement to ceiling, R.C.C. columns, beams, surface of stair case, sunshades, cornices, railings, drop wall, louvers, fins and finishing the corners and edges including washing of sand, cleaning the surface, curing at least for 7 days, cost of water, electricity, scaffolding and other charges etc. all complete in all respect as per drawing and accepted by the Engineer-in-charge. (Cement: CEM-II/B-M) | 32.39 | Sqm |  | 0
22 | Minimum 12 mm thick cement sand (F.M. 1.2) (WASH Block and MHM Pit) plaster with neat cement finishing to plinth wall with cement (1:4) up to 150 mm below ground level including washing of sand, finishing the edges and corners and curing at least for 7 days, cost of water, electricity, scaffolding and other charges etc. all complete in all respect as per drawing and accepted by the Engineer-in-charge. (Cement: CEM-II/B-M) | 12 | Sqm |  | 0
23 | Collapsible gate (Size 5'x 7'): (MS Angle at top 1.5"x1.5"x5mm with roller bearing 6 set setting at top position, MS Angle at bottom 1.5"x5mm & use MS Flat bar 1"x4mm, Vertical MS angle 1"x1"x4mm @ 4" c/c), all c fitting ,fixing, complete as per design & direction, (Making & Supply) use 1 coat red oxide paint with properly drying & 60 grade BSRM angle & flat bar | 35 | Sft |  | 0
24 | Supplying fitting & fixing of PVC Big Almirah Product Code:802770 Brand: Trendy/ RFL/ VISION Durable Eco-friendly Easy to assemble Weather resistant Anti-scratch & water proof Big almirah: (height x width x Length): 1745x385x705 mm | 1 | Each |  | 0
25 | Supplying fitting & fixing of RFL uPVC plastic door (Gold Ulka 7x2.5) fitted and fixed in brick wall with 6 Nos. GI clamp, 4 nos inner joint GI clamp, 2 nos. outer GI joint clamp, 16 nos. rivet making necessary grooves and mending good the damages, finishing, curing, carriage etc complete in all respect as per design and direction of the Engineer. | 2 | Each |  | 0
26 | Supplying fitting & fixing RFL Cosmic Door Unique (Cosmic Super Spectra Door 7'-0''x3-0''' R-TB) fitted and fixed in brick wall with 6 Nos. GI clamp, 4 nos inner joint GI clamp, 2 nos. outer GI joint clamp, 16 nos. rivet making necessary grooves and mending good the damages, finishing, curing, carriage etc complete in all respect as per design and direction of the Engineer. | 2 | Each |  | 0
27 | Supplying, fitting and fixing of aluminium sliding window (KAI/ NIKKI/ KAT/ equivalent) (1524mmx1372mm)as per the U.S. Architectural Aluminium Manufacturer’s Association (AAMA) standard specification and BDS 1879:2014 having minimum 1.2 mm thick outer bottom (size 75.50 mm, 32 mm, 0.605 kg/m), minimum 1.2 mm thick outer top (size 75.50 mm, 28.50 mm, 0.705 kg/m), minimum 1.2 mm thick shutter top (size 33 mm, 26.80 mm, 0.42 kg/m),minimum 1.2 mm thick shutter bottom (size 60mm, 24.40 mm,0.589 kg/m), minimum 1.2 mm thick outer side (size 75.50 mm, 19.90 mm, 0.52 kg/m), minimum 1.2 mm thick shutter lock (size 49.20 mm, 25.80 mm, 0.543 kg/m) and minimum 1.2 mm thick inter lock (size 34.40 mm, 32.13 mm,0.562 kg/m) sections all aluminium members will be anodized to aluminium bronze/silver/ss/black colour with a coat not less than 15 microns in thickness or powder coated to any colour with a coat not less than 25 microns in thickness and density of 4 mg per square cm etc. including all accessories like sliding door key lock (KAT/KAI), sliding door wheel (SS-KAT/KAI), sliding door mohiar sliding door neoprene, bolts (SS) and nuts (SS) including sealants, keeping provision for fitting 5 mm thick glass (NASIR/ PHP/ NAVANA) including labour charge for fitting of accessories, making grooves and mending good damages, carriage, and electricity complete in all respect as per drawing and accepted by the Engineer-incharge. | 1.86 | Sqm |  | 0
28 | Supply, fitting and fixing frosted glass paper/film on glass surface inner side of the glass full height as per direction of EIC, including cleaning, cutting, alignment, labour, transportation, contractor's profit, VAT and taxes complete in all respects. | 1.86 | Sqm |  | 0
29 | Supplying, fitting and fixing window grill made of 12 mm x 12 mm M.S. solid bar @ 100mm c/c with outer frame of 38 mm x 6mm F.I. bar and 25 mm x 6 mm F.I. bar for clamp as per design including fabrication, welding, cost of electricity workshop charges, labour charges for fitting and fixing grills in position, local carriage charges, cutting grooves, mending good the damages, tools and plants, finished with anti-corrosive painting (Red-Oxide) etc. complete for all floors approved and accepted by the Engineer-in-charge. (Total weight per sqm should be approx. 19 kg and add or deduct @ 100.00 for each kg/sqm excess or less respectively) | 2 | Sqm |  | 0
30 | Supplying,fitting and fixing High window grill with wire Mosquito Net (KAI/ NIKKI/ KAT/ equivalent) made of M.S. section approx Square bar 10mm thickness and approx Outer angle frame 25mmx25mmx4mm member as per drawing and design approved and accepted by the Engineer. (Rate is excluding the cost of enamel paint but inclusive of anti corrosive red/gery oxide paint). | 10 | Pcs |  | 0
31 | SS Railing work for Ramp: Supplying, fitting and fixing all necessary materials including labour charge (2"x 1.2mm top rail pipe & 1.5"x 1.2mm vertical post @ 3 feet c/c & 2 nos Miner boll 3" dia fitting, 3/4" x1.0mm pipe @ 4 nos at side bottom rail) as per design & direction engineer in charge (all ss pipe SKV/Steel-tech/Nihan/Equivalent brand) | 104 | Sft |  | 0
32 | SS Hand Railing work for Toilet (Girls MHM Toilet and Girls Disable Friendly Toilet): Supplying, fitting and fixing all necessary ss materials including labour charge 1.5"x 1.2mm Rail pipe. as per design & direction engineer in charge (all ss pipe SKV/Steel-tech/Nihan/Equivalent brand) | 10 | Sft |  | 0
33 | (MHM Damping pit Net) Supply, fitting & fixing of window made with MS 10mm square bar/grill and angle and good quality MS wire net, size is 2’–6” x 2’-0” | 1 | Pcs |  | 0
34 | (MHM Pit SS Cover-Door) Cover should be made by SS sheet with lock. Size is 10''-0"x 10''-0" | 1 | Pcs |  | 0
35 | (MHM Pit) 4'' Dia RCC Pipe with cowl Height-10'-0'' | 1 | Pcs |  | 0
36 | (MHM box cover -Door) Cover should be made by MS sheet with lock. Size is 1'-0"x 1'-6". | 2 | Pcs |  | 0
37 | Approved best quality and (White Colour at Celling Synthetic Polyvinyl Distemper (Berger) delivered from authorized local agent of the manufacturer in a sealed container, applying to wall and ceiling with surface preparation including cleaning drying, making free from dirt, grease, wax, removing all chalked and scaled materials, fungus, mending good the surface defects using sand paper and necessary scaffolding; applying 1 coat of interior sealer of specified brand on prepared surface; then applying 1 coat of interior putty of specified brand for levelling, spot filling, crack filling and cutting by sand paper/zero water paper; finally applying 2 coats of synthetic polyvinyl distemper spreading by brush/roller/spray & necessary scaffolding etc. up to desired finishing, elapsing specified time for drying or recoating; all complete in all floors and accepted by the Engineer-in-charge. | 32.39 | Sqm |  | 0
38 | Painting to door frames and shutters, window grills, frames and shutters and collapsible gate, outside dado wall and roof cornice in 02 coats with approved best quality and colour Synthetic Enamel Paint (Berger Green Colour must be matching with Good Neighbors Logo Colour or Green Colour Code Spring 3A0872 ) delivered from authorized local agent of the manufacturer in a sealed container, having highly water resistant, high bondibilty, flexible, using specific brand thinner applied by brass/roller/spray over a coat of priming elapsing time for drying including surface cleaning from dust, oil of dirt, smoothening, finishing and polishing with sand paper and necessary tools, scaffolding etc, All complete as approved and accepted by the Engineer | 9 | Sqm |  | 0
39 | On exterior surface applying as per manufacturer instructions 03 coats of Weather Coat (Berger Green Colour must be matching with Good Neighbors Logo Colour or Green Colour Code Spring 3A0872 ) of approved quality and colour(Outer side=old gold color & roof slab edge= Tangerine color) delivered from authorized local agent of the manufacturer in a sealed container complete in all respect in al floor as accepted by the Engineer.* | 63.87 | Sqm |  | 0
40 | On exterior surface applying as per manufacturer instructions 03 coats of Plastic Paint (Berger Green Colour must be matching with Good Neighbors Logo Colour or Green Colour Code Spring 3A0872 ) of approved quality and colour(Outer side=old gold color & roof slab edge= Tangerine color) delivered from authorized local agent of the manufacturer in a sealed container complete in all respect in all area as accepted before installation with sample checked by EIC.* | 42.3 | Sqm |  | 0
41 | Providing 600 mm wide Apron with 75 mm avg. thick cement concrete (1:2:4) with cement, coarse sand and picked jhama chips including breaking chips and one layer brick flat soling at bottom with first class or picked jhama bricks including cutting earth for preparation of bed and filling the interstices with local sand (FM 0.8) including finishing, dressing, curing at least for 7 days etc. all complete, including cost of water, electricity, other charges accepted by the Engineer. (Cement: CEM-II/A-M)* | 8 | m2 |  | 0
42 |  |  |  |  | 0
43 | Part "B" Sanitary & Plumbing Work's (All the items include VAT, Tax & profit) :
44 | Sanitary Fittings with Fixtures & Plumbing Work's (All the items include VAT, Tax & profit) :
45 | Ceramic pan with flush tank/ closet (18"x22") (RAK-25CM/Rosa/Sanita/STELLA/Equivalent) | 2 | Each |  | 0
46 | High commode (Z flush) set with water closet (size: 680x360) (RAK Resort/Rosa/Sanita/STELLA/Equivalent) automatic closing, cistern system, water Tank, moving Shower (SATTAR) ,mending good the damages and fitting, fixing, finishing etc. complete with all necessary fittings and connection approved and accepted by the Engineer- in- charge. | 1 | Each |  | 0
47 | Supply Glazed vitreous W/S Basin with Pedestal (RAK/ ROSA/ Equivalent) of Size approx..550*450*845 including Fitting fixing the same in position with Heavy type CI Brackets (SS) and Connection Pipe (RFL/ SATTAR) 38mm dia and Magic pipe (RFL/ SATTAR), Angle Stop Cock (SELINA/ SATTAR/ SOJEN) ,Mirror (NAVANA/ PHP/ NASIR/ equivalent) and other necessary Materials, Fitting ,fixing ,carrying. Acceptable by the Engineer. | 2 | Each |  | 0
48 | Supplying, fitting and fixing 100 mm dia uPVCTrap ('P' Trap or 'S' Trap) and uPVC door bend/tee (National Polymer/RFL/Equivalent brand) including making holes in walls and floors and mending good the damages etc. All complete approved and accepted by the Engineer.. | 3 | Each |  | 0
49 | Supplying, fitting and fixing 125 mm dia S.S Gratings/Net (SHAHNOOR/ SATTAR/ SELINA) in traps or in drains with cement mortar (1:4) including making holes in walls and floors and mending good the damages etc. all complete as per direction of the Engineer in charge. | 3 | Each |  | 0
50 | Supplying, fitting and fixing super quality SS Towel rail of 600 mm long and 20 mm in dia with holder including making holes in walls and mending good the damages with cement mortar (1:4) etc. all complete approved and accepted by the Engineer. | 3 | Each |  | 0
51 | Supplying, fitting and fixing of special coloured PVC Toilet paper holder (SHINE/ MATADOR/ARABIAN/ Equivalent) Size (150 mm x 150 mm x 126 mm) including making holes in walls and mending good the damages with cement mortar (1:4) etc. all complete approved and accepted by the Engineer. | 3 | Each |  | 0
52 | Supplying, fitting and fixing size L 165 x W 125 x H 110MM Made from highly shiny grade ABS material good quality Easy to install, load & use Made with state of art technology & unique design. SS C.P Soap Tray including making holes in walls and mending good the damages with cement mortar (1:4) etc. all complete approved and accepted by the Engineer. | 6 | Each |  | 0
53 | Supplying, fitting, fixing 1" and 3/4'' dia cpvc pipe (Concealed Wiring) (National Polymer/RFL/Equivalent brand) best quality pipe, wall thickness 4.2mm, pipe must be straight & uniform thickness, free from any defects such as cracks, rupture, leak, etc. All complete approved and accepted by the Engineer. | 1 | LS |  | 0
54 | Supplying,fiting and fixing SS Bib Cock good quality tap. Made by Sattar/Sojen/ selina. all complete approved and accepted by the Engineer. | 4 | Pcs |  | 0
55 | Supplying,fiting and fixing SS Basin Pillar Cock good quality tap. Made by Sattar/Sojen/ selina. all complete approved and accepted by the Engineer. | 2 | Pcs |  | 0
56 | Supplying, fitting and laying up to depth of 100 mm inside dia best quality uPVC C-grade Soil Pipe having specific gravity 1.3-1.45, and other physical, chemical, thermal, fire resistivity properties etc. as per BSTI approved manufacturer standards or ASTM, BS/ISO/IS standards fitted and fixed in position with sockets, bends, with all accessories such as Round grating/domed roof grating etc. All complete approved and accepted by the Engineer. uPVC soil pipe 100 mm inside dia wall thickness 3.4- 4.0 mm | 20 | RM |  | 0
57 | Supply, carrying, installation, testing and commissioning of 500 Litre Gazi Water Tank (MODINA/GAZI) Type: Vertical Cylindrical Water Storage Tank, Capacity: 500 Litres (0.50 m³), Material: Food-grade Virgin Polyethylene (LLDPE/HDPE), Manufacturing Process: Rotational Moulding (Roto Moulded), Colour: Black, Blue, Green or White (UV stabilized), Application: Overhead and Ground Water Storage, Layers: Minimum 3 Layers (preferably 4 Layers), Outer UV Resistant Layer, Structural Middle Layer, Food Grade Inner Layer, Wall Thickness: Minimum 4.0–6.0 mm (depending on manufacturer), UV Protection: UV Stabilized for outdoor installation, Corrosion Resistance: 100% Rust Free, Leak Proof: Seamless one-piece moulded construction, Diameter 800–900 mm, 1000–1200 mm (H) Fittings: Inlet Connection: 25 mm (1"), Outlet Connection: 25 mm (1"), Overflow Connection: 25–32 mm, Drain/Washout Connection: 25 mm Screw Type Lid with Ventilation Arrangement, 3-layer UV-stabilized food-grade tank with minimum 12 kg weight and 500 L capacity complete with included accessories including float valve, inlet-outlet connection, ball valve, overflow pipe, washout arrangement, tank connector, uPVC fittings, solvent cement, labour, transportation,all necessary fittings, connection to existing pipeline for one storied building from top to bottom with connection of existing delivery pipe line, including transportation, labour, contractor's profit, VAT and taxes: | 1 | Nos. |  | 0
Sub-Total of B1 = |  |  |  |  | 0
B2.
48 | Construction of septic tank
Sub-Total of B2 = |  |  |  |  | 0
Total (B1+B2) = |  |  |  |  | 0
C. | INTERNAL ELECTRIFICATION (All the items included VAT, Tax & profit) :
CONCEALED CONDUIT WIRING
57 | Concealed conduit wiring supplying, fixing & fitting etc. all complete for the following point looping at the switch board with earth terminal including circuit wiring with 1C-2X1.5 sqm PVC insulated cable (BYA) & 1.5 sqm PVC insulated green / white coloured ECC wire (BYA) through PVC conduit (Lira brand or equivalent product of other reputed manufacturer) of minimum 20 mm dia & 1.5 mm wall thickness 18 SWG GP sheet, switch board and pull box with 3 mm thick ebonite sheet cover, 5 amps, piano switch, ceiling rose, fixing materials etc. as required (all electrical contacts shall be of brass / copper) mending the damages goods.
| (a) 20mm dia, 1.5mm Thick PVC pipe for conceal conduting | 20 | Rm |  | 0
| (b) Double core insulated electric wire (3/20) ( Estern/BRB/Paradise/equivalent) for internal connection | 22 | Rm |  | 0
| (c) Light points and multi holder (screw & pin) | 6 | Point |  | 0
| (d) LED Bulb 12W Pin Type Superstar/ eg | 6 | Point |  | 0
58 | SP CIRCUIT BREAKER |  |  |  | 0
59 | Circuit Breaker with Box 16 Amp (Double Pole) (Superstar/ eg/ legrand) | 1 | Nos |  | 0
60 | GANG SWITCH |  |  |  | 0
| Supplying ,fixing & fitting etc. all complete using 250 volts. 5 amps (minimum) concealed type following switch / switch socket mounted on required size 18 SWG galvanized plain sheet board of 76.2 mm (3") depth all electrical contact shall be brass / copper gang switch of following brand & country of origin. (MK England or equivalent product as approved by the Engineering in charge. |  |  |  | 0
61 | Gang switch (eg/energy pac/ walton) | 10 | Nos |  | 0
62 | 2 & 3 pin multi socket with switch (eg/energy pac/ walton) | 2 | Nos |  | 0
63 | Double core insulated electric wire (7/20) ( Estern/BRB/Paradise/AKIJ/BBS) for connection with electric service from Main power supply to SDB and Pump. All complete as per standard practice and accepted by the Engineer in charge. | 25 | Rm |  | 0
Sub-Total C= |  |  |  |  | 0
Water supply with submersible pump (All the items include VAT, Tax & profit): Average Depth: 100 m maximum
64 | Mobilization of materials, equipment, tools & plants, casing pipe and boring rig to work site. Construction of derrick and dismantling the same, leveling, cleaning the site after completion of the work as per direction of the Engineer-in-Charge.. | 1 | No. |  | 0
65 | Boring and installation of uPVC pipes and fittings for tube well : Boring by using 200/100 mm dia cutter and 50 mm dia GI pipe and other equipment capable of drilling up to a depth of 200 m by water jet system through all sorts of strata, protection of caving by supplying necessary casing pipe, collection of soil samples at every 3 m interval, every change of strata and preserve them for analysis, withdrawal of boring pipes & casing pipes with completed successful tube well etc. as per specifications and direction of the Engineer-in-Charge. |  |  |  | 0
a | From 0m - 50m (Using 200mm dia cutter) Upvc Pipe class 'D' (RFL/ NATIONAL/ GAZI) | 50 | M |  | 0
b | From 50m - 100m (Using 100mm dia cutter) Upvc Pipe class 'D' (RFL/ NATIONAL/ GAZI) | 50 | M |  | 0
66 | Supplying and installation of 100/50 mm dia water grade uPVC pipe having wall thickness 3.0 m to 3.5 mm 'D' Class of approved quality, uPVC sand trap of length 3.0 m with cap, uPVC strainer of designed slot installing at the middle of the most suitable water bearing strata. Upper 30 meter will be 100 mm uPVC thread pipe joining with 50 mm uPVC pipe by a 100 X 50 mm uPVC best quality reducer. Fixing of 100 mm dia GI pipe at the top of 100 dia uPVC pipe, all complete as per direction of the Engineer-in-Charge. (The cost will include solvent cement, material cost, thread tape, labor charge, carrying charge of all materials and all equipment's to the sites). |  |  |  | 0
67 | From 0.0 m to 1.5 m 100 mm GI Pipe with a socket (3.65mm thick) | 1.5 | M |  | 0
a | From 1.5 m to 31.5 m 100 mm uPVC thread pipe (Class 'D') (RFL/ NATIONAL/ GAZI) | 40 | M |  | 0
b | From 100 x 50 mm uPVC reducer (RFL/ NATIONAL/ GAZI) | 1 | Each |  | 0
c | 50 mm dia water grade uPVC Pipe and Sand Trap (PN 12 / Class "D") of approved quality by EIC (RFL/ NATIONAL/ GAZI) | 60 | M |  | 0
d | 50 mm dia water grade uPVC Super Strainer with 10 slot (PN 12 / Class "D") of approved quality by EIC (RFL/ NATIONAL/ GAZI) | 18 | M |  | 0
e | 50 mm dia PVC cap (RFL/ NATIONAL/ GAZI) | 1 | M |  | 0
f | Filling the borehole with coarse sand (FM 2.5) upto 10m from the top of filter. | 33 | M |  | 0
g | Filling of the bore-hole around the tube well from top of the shrouding up to the bottom of sanitary seal by withdrawn selected soil or local clay free from any substances harmful to pipes and health as per standard specification and accepted by the Engineer-in-charge | 67 | M |  | 0
h | Cement sealing or clay pack on the top of coarse sand fill by inserting cement slurry (1:1 by weight of cement and water)/dropping clay ball made of 50% puddle clay and 50% bentonite from top. Simultaneously filling all gaps (plumbing, sanitary) with putty/ white cement by direction of EIC. | 0.5 | M |  | 0
68 | Complete development of the tube well to obtain sand & turbidity free water at a satisfactory yield, etc. all complete as per specifications and direction of the Engineer-in-Charge. | 1 | each |  | 0
69 | TW Disinfections: Disinfection of well by bleaching power (33% strength) including supply of sufficient quantity, making chlorinated water having 150 mg/l available free chlorine and applying to the tube well. After 24 hrs of retention, chlorinated well water to be pumped out until chlorine free clear water is reached etc all complete as per specification and direction of EIC. | 1 | L.S |  | 0
70 | Protective top cover: Supplying and fitting fixing best quality 200 mm dia 4 mm thick M.S. pipe 1.0 m (3'-4") long, one end blocked with 250 mm dia 4 mm thick M.S. plate and other end minimum 300 mm (1'-0) embedded in sanitary seal for protection of uPVC housing pipe as per standard specification and accepted by the Engineer-in-charge. | 1 | each |  | 0
71 | Supply, fitting and fixing of appropriate Submersible pump Horse Power: 1.50, VOLTAGE: 180V-220V, HEAD (METER): 35-62m, CAPACITY(LIT/MIN): 60-100 L, DELIVERY: 1 to 1 1/2", including top base plate, suspension cables, switching control panel etc, all complete as per direction of E-I-C. (The Contractor must supply the manufacturer's pump curve, before final approval from E-I-C). | 1 | Each |  | 0
72 | Supplying & installation of PVC insulated & sheeted cable (BYFYE) channeled through 20mm dia uPVC pipe. Complete with all other accessories, Manufacturer of cable Eastern/BRB or equivalent according to the Specification & direction of the Engineer-in-Charge. 3C-2.5 Sq. mm (BYFYE) Cable | 20 | RM |  | 0
73 | Pipe Working (all types) |  |  |  | 0
74 | Earthwork in all excavation of trench for laying pipes, inspection pit etc., by excavating earth to the lines, grades and direction as shown in the drawings, filling the baskets, carrying and disposing of all excavated materials at a safe distance designated by the Engineer-in-charge in all types of soils including levelling, dressing etc. all complete for an initial excavation depth of 0.45m and an initial lead not exceeding 5m and backfilling the same once after laying of pipes, all complete as per direction of Engineer-in-Charge. | 700 | RM |  | 0
75 | Supplying, fitting and fixing 25mm inside dia best quality HDPE C-grade coil pipe for water supply having specific gravity 1.35-1.45, and other physical, chemical, thermal resistivity properties etc., as per BSTI approved manufacturer standars fitted and fixed in position with all requisite sockets, bends, with all accessories, all complete as per direction of E-i-C. | 700 | RM |  | 0
Sub-Total D= |  |  |  |  | 0
E. | Others (All the items include VAT, Tax & profit):
76 | Supplying and installation of Regal PATIENT EXAMINATION BED (Hospital) MBE-507,Product Code: 882818. - Tow section top with head adjustable on rachet. - Rexine covered cushioned bed on top. - Body made of MS pipes. - All epoxy powder coated or de-rusted zinc phosphate baked enamel finished. - Head portion raised or lowered by ratchet arrangement. - Top covered with rexie & feet ends with solid rubber/PVC stoppers. | 1 | Item |  | 0
77 | Supplying, fitting and installation of Inscribing (writing) the name plate of the Project and other necessary information in English by laser print with emboss on outside front face of the Public toilet with approved quality Marble stone (Italian Karaka, special quality), size 12"x18", Thickness 15mm, four color approved sample by EIC before installation and others direction. | 1 | Item |  | 0
78 | Supplying, fitting and fixing printed pvc board informative sign of the size 2ft x3ft by wooden frame with wooden post to be placed at as per direction. | 2 | Each |  | 0
79 | Supply, Fitting and Fixing printed pvc board informative sign of the Size 15ft x12 inch to be placed at as per direction. | 1 | Each |  | 0
80 | Water Purifier-Unilever Pure it Classic ,Capacity: 23 L | 1 | Each |  | 0
81 | Unilever Germ kill Kit - Classic GKK 3000Ltr | 1 | Each |  | 0
82 | Vision Drink it Stand (3 Step) | 1 | Each |  | 0
83 | RFL Moushumi Jug 2.2L and Italiano Smart Glass Lilac | 1 | Each |  | 0
Sub-Total E = |  |  |  |  | 0
Summary of Public toilet Unit Estimate (Running water supply using Submersible pump) (All the items include VAT, Tax & profit):
A. | Civil Works of Building |  |  |  | 0
B. | Sanitary & Plumbing Work's |  |  |  | 0
C. | Internal Electrification |  |  |  | 0
D. | Running water supply using Submersible pump |  |  |  | 0
E. | Others |  |  |  | 0
Total cost of 01 no Public Toilet BDT. = |  |  |  |  | 0
Total cost of 3 no Public Toilet BDT. = |  |  |  |  | 0
In words (BDT.) :
*/**/*** Note: All materials, tools, quipments and works quality check by EIC before installation, supply and fitting-fixing and Contractor/ vendor will bear any types of cost of remaining materials/ equipments for fitting/ fixing / installation a completed successful WFT (Women Freiendly Toilet) included all things with standard quality.